## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
CM_01 | US:101 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Sai Aravind | 13/7/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Sai Aravind | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Sai Aravind | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Sai Aravind | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Sai Aravind | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.
CM_02 | US:102 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Sindhuja | 13/07/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Sindhuja | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Sindhuja | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Sindhuja | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Sindhuja | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.
CM_04 | US:104 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Sai Prasad, soumya | 13/07/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Sai Prasad, soumya | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Sai Prasad, soumya | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Sai Prasad, soumya | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Sai Prasad, soumya | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.
RM_01 | US:105 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Sneha | 13/07/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Sneha | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Sneha | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Sneha | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Sneha | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.
RM_02 | US:106 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Mohan Vamshi | 13/07/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Mohan Vamshi | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Mohan Vamshi | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Mohan Vamshi | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Mohan Vamshi | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.
RM_03 | US:107 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Pooja Nandana | 13/07/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Pooja Nandana | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Pooja Nandana | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Pooja Nandana | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Pooja Nandana | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.
CM_03 | US:103 | 1 | Understanding the work flow and analyzed the dependent variables involved in different modules of the project for individual case studies of the team members. | Pravalika | 13/07/2020 | 1 day | 1 day | Completed | 1 day | understood the work flow of the project, and implemented the entity classes with relations.
|  | 2 | implemented RestAPIs and tested their working | Pravalika | 14/7/2020 | 1.5days | 1.5days | Completed | 1.5days | Implemented RestAPIs and tested their working using postman
|  | 3 | Implementing Junit Test cases | Pravalika | 15/07/2020 | 0.5 day | 0.5 day | Completed | 0.5 day | Implemented junit test cases for each functionality.
|  | 4 | ExcpetionHandling and validations | Pravalika | 16/07/2020 | 1 day | 1 day | Completed | 1 day | implemented global level exception handling.
|  | 5 | Worked on integration of the whole project | Pravalika | 17/07/2020 | 1.5 days | 1.5 days | Completed | 1.5 days | completed the integration of all the individual case studies.

## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | CM_01 | Create a Customer | M | US: 101 | When a customer gets registered by entering all the required details | Customer | Customer management and review management | medium | Analysing the workflow of project without any duplicate customers and maintaing unique details | Taken Reference from case study | Customer will access and enters the details from frontend to perform the required operation and store the customer details in the backend | [5 empty] | required |  | This is used to add the customer details with a unique mail Id for each customer added into the system
2 | CM_02 | List all Customer | M | US: 102 | Displaying all the customers who got registered | Admin | Customer management and review management | medium | Analysing the workflow of project to diplay all the customer details who got registered | Taken Reference from case study | Admin List all the customers who got registered with unique mail id and with details required from backend to to display in the frontend | [5 empty] | required |  | This is used to list all the customers who got registered into the system
3 | CM_03 | Edit Customer | M | US: 103 | Editing the customer details provided | Customer | Customer management and review management | medium | Analysing the workflow of project to edit a particular customer details | Taken Reference from case study | Cutomer can edit his details provided while registration through fronted | [5 empty] | required |  | This is used to update customer details or edit the details given
4 | CM_04 | Delete Customer | M | US: 104 | Deleting the customer details | Admin | Customer management and review management | medium | Analysing the workflow of project to delete a particular customer details by checking previous orders and reviews | Taken Reference from case study | Admin has to check the details of the customers i.e if has purchased any book or if he reviwed any book before deleting the customer | [5 empty] | required |  | This isused to delete the customer details who got registered
5 | CM_05 | Delete review | M | US: 105 | Deleting the review of a customer | Admin | Customer management and review management | medium | Analysing the workflow of project and deleting the review if customer violtaes the rules | Taken Reference from case study | Admin has to check the review of the customer if there is any violation in the comment then the review should be deleted | [5 empty] | required |  | This is used to delete a review given by customer
6 | CM_06 | Update a review | M | US: 106 | Update a review of a customer | Admin | Customer management and review management | medium | Analysing the workflow of project to update the review headline and comment of a particular review | Taken Reference from case study | Admin can update the customers review.he can update only comments and headlines in the review | [5 empty] | required |  | This is used to update the review of a customer given
7 | CM_07 | List all reviews | M | US: 107 | Displaying all the customers reviews | Admin | Customer management and review management | medium | Analysing the workflow of project to diplay all the customers review | Taken Reference from case study | Admin List all the reviews given by the customers and displays them in the frontend | [5 empty] | required |  | This is used to list all the customers reviews given