## User stories
| Main User Story | Sub-Task
1 | Customer Management | List all Customers
Create Customer
Delete Customer
Edit Customer
2 | Review Management | List all Reviews
Delete Review
Update Review

## Sai Aravind
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
1 | Customer Management
1.1 | Create Customer
1.1.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
1.1.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
1.1.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
1.1.4 | Exception handling and validations | 1 | 1 | Thursday
1.1.5 | Integration | 1.5 | 1.5 | Friday

## Sindhuja
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
1 | Customer Management
1.2 | List all Customer
1.2.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
1.2.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
1.2.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
1.2.4 | Exception handling and validations | 1 | 1 | Thursday
1.2.5 | Integration | 1.5 | 1.5 | Friday

## Pravalika
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
1 | Customer Management
1.3 | Update Customer
1.3.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
1.3.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
1.3.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
1.3.4 | Exception handling and validations | 1 | 1 | Thursday
1.3.5 | Integration | 1.5 | 1.5 | Friday

## Sai Prasad & Soumya
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
1 | Customer Management
1.4 | Delete Customer
1.4.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
1.4.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
1.4.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
1.4.4 | Exception handling and validations | 1 | 1 | Thursday
1.4.5 | Integration | 1.5 | 1.5 | Friday

## Mohan Vamshi
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
2 | Review Management
2.1 | Update Review
2.1.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
2.1.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
2.1.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
2.1.4 | Exception handling and validations | 1 | 1 | Thursday
2.1.5 | Integration | 1.5 | 1.5 | Friday

## Sneha
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
2 | Review Management
2.2 | List all Review
2.2.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
2.2.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
2.2.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
2.2.4 | Exception handling and validations | 1 | 1 | Thursday
2.2.5 | Integration | 1.5 | 1.5 | Friday

## Pooja Nandana
Task No. | Task Name | Estimated Days | Actual Time Taken | Allotted on day | Comments
2 | Review Management
2.3 | Delete Review
2.3.1 | Understanding User Requirements and Design Diagaram | 1 | 1 | Monday
2.3.2 | Design Backend Data Structure | 1.5 | 1.5 | Tuesday
2.3.3 | Implementing Junit Test Cases | 0.5 | 0.5 | Wednesday
2.3.4 | Exception handling and validations | 1 | 1 | Thursday
2.3.5 | Integration | 1.5 | 1.5 | Friday